## Risks
Hungerger Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2023-11-03 | Intellectual Property | Potential legal challenges regarding the ownership and use of recipes shared by users on the platform. | Business | 4 | 40% | 1.6 | Team | Clearly define terms of service and user agreements, specifying rights and ownership of user-generated content.
2 | 2023-11-03 | User Engagement | Risk that the platform may not engage users as expected, leading to a lower-than-anticipated number of active users and recipe contributions. | Business | 5 | 30% | 1.5 | Team | Conduct user surveys and feedback sessions to understand their needs and preferences. Iterate on UI/UX based on feedback.
3 | 2023-11-03 | Integration Complexity | Difficulties in integrating with various marketplace APIs for cost calculation features, leading to delays or reduced functionality. | Technical | 2 | 55% | 1.1 | Abdullah | Collaborate with API providers for technical support and documentation. Perform integration testing early in the development cycle to identify and address issues.
4 | 2023-11-03 | Content Quality | Dependence on influencers and users to generate high-quality content, with the risk of low-quality or inappropriate content affecting the platform's reputation. | Business | 3 | 30% | 0.9 | Abdullah | Establish content guidelines. Provide resources for influencers on creating quality content. Consider partnerships with experienced content creators.
5 | 2023-11-03 | Resource Availability | Risk of key personnel or technical expertise being unavailable when needed, causing project delays. | Resource | 4 | 20% | 0.8 | Tarık | Maintain comprehensive documentation to allow easy onboarding. Consider hiring consultants or short-term experts when needed.
6 | 2023-11-03 | Data Security | Risk of data breaches or loss, particularly concerning user password storage and personal information, despite using secure hashing and encryption. | Technical | 5 | 15% | 0.75 | Tarık | Implement multi-layered security measures. Employ a Zero Trust model. Conduct regular employee training on data security. Backup data regularly and ensure a rapid disaster recovery plan is in place.
7 | 2023-11-03 | Compliance with Data Protection | Risk of failing to comply fully with KVKK and GDPR, which could result in legal penalties and loss of user trust. | Business | 5 | 15% | 0.75 | Merve | Consult with legal experts familiar with these regulations. Regularly audit and update data collection, storage, and sharing practices.
8 | 2023-11-03 | Scalability | Potential challenges in scaling the system to accommodate a growing number of users and data volume, which could affect performance. | Technical | 3 | 20% | 0.6 | Abdullah | Use cloud-based solutions that allow scaling based on demand. Regularly review infrastructure needs and optimize database queries.
9 | 2023-11-03 | Performance | Risk that the system may not consistently achieve sub-second response times, leading to user dissatisfaction. | Technical | 3 | 20% | 0.6 | Aslı | Monitor system performance metrics regularly. Optimize code and database queries. Run regular stress and load tests.
10 | 2023-11-03 | Timeline and Budget | Risk of project overruns in terms of time and budget due to unforeseen complexities or scope changes. | Schedule | 3 | 15% | 0.45 | Aslı | Adopt agile methodologies to adapt to changes efficiently. Establish clear scopes and requirements.
11 | 2023-11-03 | Multi-language Support | Delays or difficulties in implementing multi-language support, potentially limiting the platform’s appeal in non-English speaking regions. | Business | 2 | 15% | 0.3 | Merve | Utilize translation services or tools. Engage native speakers for quality checks.
Note on E2: ====== ID#AAAA_CC9f-Q rbalduino (2023-10-29 10:13:37) Risk Type = Direct or Indirect Resource Business Technical Schedule
Note on F2: ====== ID#AAAA_CC9f-U mbarnard (2023-10-29 10:13:37) Impact is a numerical value, usually between 1 and 5, that represents the impact to the project if the risk comes true. 5 is a HIGH IMPACT and 1 is LOW IMPACT.
Note on G2: ====== ID#AAAA_CC9f-c mbarnard (2023-10-29 10:13:37) Probability is the percentage chance that a risk will occur.
Note on H2: ====== ID#AAAA_CC9f-Y mbarnard (2023-10-29 10:13:37) Magnitude is the result of the multiplication of Probability and Impact, providing a joint metric suitable for sorting.