## Sheet1
Work-Item ID | Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
HGG01 | Prepare Iteration Plan for Iteration 1 | 1 | 2 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | iteration1_plan_Hungerger.docx
HGG02 | Prepare Use Case Modelling | 1 | 5 | Done | 2023-01-01 | Aslı | 0 | 2 | uc_specification_Brief.docx, uc_specification_fullyDressed.docx
HGG03 | Prepare Vision Document | 1 | 8 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 3 | Vision_Hungerger.docx
HGG04 | Prepare System Wide Requirements | 1 | 5 | Done | 2023-01-01 | Tarık | 0 | 2 | systemwide_req_spec.docx
HGG05 | Deciding on Supplementary Requirements | 1 | 3 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | systemwide_req_spec.docx
HGG06 | Prepare Project Plan | 1 | 5 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 2 | Project_Plan_Hungerger.docx
HGG07 | Prepare Risk List Document | 1 | 3 | Done | 2023-01-01 | Merve | 0 | 1 | risk_list.tpl.xlsx
HGG08 | Prepare Work Items List Document | 1 | 3 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
HGG09 | Prepare Glossary | 1 | 3 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | Glossary_Hungerger.docx
HGG10 | Prepare Iteration Plan for Iteration 2 | 1 | 2 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | iteration1_plan_Hungerger.docx
HGG11 | Decide the architecture | 1 | 5 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 2
HGG12 | Create the database | 1 | 8 | Done | 2023-02-01 | Merve | 0 | 5
HGG13 | Create the Entity Relation Diagram | 1 | 3 | Done | 2023-02-01 | Merve | 0 | 1
HGG14 | Design the relational model | 1 | 5 | Done | 2023-02-01 | Merve | 0 | 2
HGG15 | Create MySQL database (users,recipes,ingredients tables) | 1 | 5 | Done | 2023-02-01 | Merve | 0 | 2
HGG16 | Design the interface | 1 | 5 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 2
HGG17 | Create user register page | 1 | 3 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2 | systemwide_req_spec.docx
HGG18 | Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG19 | Do the implementation | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
HGG20 | Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG21 | Create login page | 1 | 3 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2 | systemwide_req_spec.docx
HGG22 | Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG23 | Do the implementation | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
HGG24 | Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG25 | Create Account | 1 | 8 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 5 | uc_specifications.docx
HGG26 | Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
HGG27 | Do the implementation | 1 | 5 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 3
HGG28 | Do the testing | 1 | 2 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
HGG29 | Create Recipe Feed (Homepage) | 1 | 8 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 5 | systemwide_req_spec.docx
HGG30 | Prototype UI | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
HGG31 | Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
HGG32 | Do the implementation | 1 | 5 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2
HGG33 | Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
HGG34 | Create recipe | 1 | 5 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 3 | uc_specifications.docx
HGG35 | Prototype UI | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG36 | Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG37 | Do the implementation | 1 | 2 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2023-05-01
HGG38 | Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
HGG39 | Prepare Iteration Plan for Iteration 3 | 1 | 2 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
HGG40 | Finish creating MySQL database | 1 | 5 | Done | 2023-03-01 | Merve | 4 | 0
HGG46 | Predefine some admin users | 2 | 2 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | systemwide_req_spec.docx
HGG47 | Authorize admins | 2 | 3 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 7 | 0 | systemwide_req_spec.docx
HGG48 | Admins should be able to create new admin user | 2 | 3 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG49 | Admins should be able to edit user | 2 | 3 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG50 | Admins should be able to delete user | 2 | 1 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG51 | Admins should be able to edit recipe | 2 | 3 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG52 | Admins should be able to delete recipe | 2 | 1 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 11 | 0
HGG55 | Edit recipe | 2 | 3 | Done | 2023-03-01 | Abdullah, Tarık | 2 | 0 | uc_specifications.docx
HGG56 | Do the design | 1 | 1 | Done | 2023-03-01 | Abdullah, Tarık | 0.5 | 0
HGG57 | Do the implementation | 1 | 1 | Done | 2023-03-01 | Abdullah, Tarık | 2023-05-01 | 0
HGG58 | Do the testing | 1 | 1 | Done | 2023-03-01 | Abdullah, Tarık | 0.5 | 0
HGG59 | Prepare Iteration Plan for Iteration 4 | 1 | 2 | Done | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG60 | Delete recipe | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 2 | 0 | uc_specifications.docx
HGG61 | Do the design | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 0.5 | 0
HGG62 | Do the implementation | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 2023-05-01 | 0
HGG63 | Do the testing | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 0.5 | 0
HGG64 | Logout Functionality | 1 | 3 | New | 2023-04-01 | Abdullah, Tarık | 3 | 0 | systemwide_req_spec.docx
HGG65 | Do the design | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
HGG66 | Do the implementation | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
HGG67 | Do the testing | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
HGG68 | Display recipe details | 2 | 3 | New | 2023-04-01 | Abdullah, Tarık | 2 | 0 | systemwide_req_spec.docx
HGG69 | Do the design | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
HGG70 | Do the implementation | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
HGG71 | Do the testing | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
HGG72 | Prepare Iteration Plan for Iteration 5 | 1 | 2 | New | 2023-04-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG53 | Create recipe | 2 | 1 | Planned | 45017 | Abdullah, Tarık | 1 | 2
HGG54 | Users shall able to create a recipe with an image | 2 | 1 | Planned | 45017 | Abdullah, Tarık | 1 | 2
HGG73 | Delete profile | 1 | 8 | New | 2023-01-02 | Abdullah, Tarık | 5 | 0
HGG74 | Do the design | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
HGG75 | Do the implementation | 1 | 5 | New | 2023-01-02 | Abdullah, Tarık | 3 | 0
HGG76 | Do the testing | 1 | 2 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
HGG77 | View profile | 1 | 8 | New | 2023-01-02 | Abdullah, Tarık | 5 | 0
HGG78 | Do the design | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
HGG79 | Do the implementation | 1 | 5 | New | 2023-01-02 | Abdullah, Tarık | 3 | 0
HGG80 | Do the testing | 1 | 2 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
HGG81 | Follow a user | 1 | 3 | New | 2023-01-02 | Abdullah, Tarık | 2 | 0 | uc_specifications.docx
HGG82 | Do the design | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 0.5 | 0
HGG83 | Do the implementation | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
HGG84 | Do the testing | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 0.5 | 0
HGG85 | Admins should be able to send system-wide notifications | 2 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0
HGG86 | Create password reset page. | 2 | 7 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0
HGG87 | Do the design | 2 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG88 | Do the implementation | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
HGG89 | Do the testing | 2 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG90 | Update profile (Edit) | 2 | 8 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0 | uc_specifications.docx
HGG91 | Do the design | 2 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG92 | Do the implementation | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
HGG93 | Do the testing | 2 | 2 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG94 | Search and filter recipe (Browse) | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0 | uc_specifications.docx
HGG95 | Comment recipe | 2 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | uc_specifications.docx
HGG96 | Rate recipe | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | uc_specifications.docx
HGG97 | Create a user settings page. | 3 | 7 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0
HGG98 | Do the design | 3 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG99 | Do the implementation | 3 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
HGG100 | Do the testing | 3 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG101 | Calculate recipe costs | 3 | 8 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0 | systemwide_req_spec.docx
HGG102 | Show recipe costs | 3 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | systemwide_req_spec.docx
HGG103 | Save a recipe for offline viewing | 4 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0
HGG104 | Prepare Iteration Plan for Iteration 6 | 1 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG105 | System availability | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 4 | 0 | systemwide_req_spec.docx
HGG106 | Monitor server uptime | 1 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG107 | Set up automated alerts for any system downtime | 1 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG108 | Implement regular database backups | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG109 | Do the testing | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG110 | System performance | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | systemwide_req_spec.docx
HGG111 | Optimize server response times | 1 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG112 | Perform regular stress and load tests | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG113 | Do the testing | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG114 | Admins should be able to view all user activity logs | 2 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG115 | Admins should have a dashboard for monitoring system metrics | 2 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG116 | Send a DM to a user | 2 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0 | systemwide_req_spec.docx
HGG117 | System notifications | 2 | 8 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | uc_specifications.docx
HGG118 | Admins should be able to reply to complaints | 3 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG119 | Report misuse | 3 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0 | uc_specifications.docx
HGG120 | Request to be a verified account | 4 | 2 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG121 | Admin verifies account requests | 4 | 2 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | uc_specifications.docx
HGG122 | Create a bonus system for the influencers | 5 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
HGG41 | Ensure database security | 1 | 8 | Planned | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | systemwide_req_spec.docx
HGG45 | Ensure HTTPS security | 1 | 5 | Planned | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | systemwide_req_spec.docx
HGG42 | User passwords should have a secure hashing algorithm | 1 | 5 | In Progress | 44986 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG43 | Database should be encrypted | 1 | 8 | In Progress | 44986 | Abdullah, Aslı, Merve, Tarık | 1 | 0
HGG44 | Do the testing | 1 | 5 | In Progress | 44986 | Abdullah, Aslı, Merve, Tarık | 1 | 0

## Sheet2
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01