## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Prepare Iteration Plan for Iteration 1 | 1 | 2 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | iteration1_plan_Hungerger.docx
Prepare Use Case Modelling | 1 | 5 | Done | 2023-01-01 | Aslı | 0 | 2 | uc_specification_Brief.docx, uc_specification_fullyDressed.docx
Prepare Vision Document | 1 | 8 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 3 | Vision_Hungerger.docx
Prepare System Wide Requirements | 1 | 5 | Done | 2023-01-01 | Tarık | 0 | 2 | systemwide_req_spec.docx
Deciding on Supplementary Requirements | 1 | 3 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | systemwide_req_spec.docx
Prepare Project Plan | 1 | 5 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 2 | Project_Plan_Hungerger.docx
Prepare Risk List Document | 1 | 3 | Done | 2023-01-01 | Merve | 0 | 1 | risk_list.tpl.xlsx
Prepare Work Items List Document | 1 | 3 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
Prepare Glossary | 1 | 3 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | Glossary_Hungerger.docx
Prepare Iteration Plan for Iteration 2 | 1 | 2 | Done | 2023-01-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1 | iteration1_plan_Hungerger.docx
Decide the architecture | 1 | 5 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 2
Create the database | 1 | 8 | Done | 2023-02-01 | Merve | 0 | 5
Create the Entity Relation Diagram | 1 | 3 | Done | 2023-02-01 | Merve | 0 | 1
Design the relational model | 1 | 5 | Done | 2023-02-01 | Merve | 0 | 2
Create MySQL database (users,recipes,ingredients tables) | 1 | 5 | Done | 2023-02-01 | Merve | 0 | 2
Design the interface | 1 | 5 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 2
Create user register page | 1 | 3 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2 | systemwide_req_spec.docx
Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Do the implementation | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Create login page | 1 | 3 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2 | systemwide_req_spec.docx
Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Do the implementation | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Create profile | 1 | 8 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 5 | uc_specifications.docx
Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
Do the implementation | 1 | 5 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 3
Do the testing | 1 | 2 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
Create Recipe Feed (Homepage) | 1 | 8 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 5 | systemwide_req_spec.docx
Prototype UI | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
Do the implementation | 1 | 5 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2
Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 1
Create recipe | 1 | 5 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 3 | uc_specifications.docx
Prototype UI | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Do the design | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Do the implementation | 1 | 2 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 2023-05-01
Do the testing | 1 | 1 | Done | 2023-02-01 | Abdullah, Tarık | 0 | 0.5
Prepare Iteration Plan for Iteration 3 | 1 | 2 | Done | 2023-02-01 | Abdullah, Aslı, Merve, Tarık | 0 | 1
Finish creating MySQL database | 1 | 5 | Planned | 2023-03-01 | Merve | 4 | 0
Ensure database security | 1 | 8 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | systemwide_req_spec.docx
User passwords should have a secure hashing algorithm | 1 | 5 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Database should be encrypted | 1 | 8 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Do the testing | 1 | 5 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Ensure HTTPS security | 1 | 5 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | systemwide_req_spec.docx
Predefine some admin users | 2 | 2 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | systemwide_req_spec.docx
Authorize admins | 2 | 3 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 7 | 0 | systemwide_req_spec.docx
Admins should be able to create new admin user | 2 | 3 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admins should be able to edit user | 2 | 3 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admins should be able to delete user | 2 | 1 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admins should be able to edit recipe | 2 | 3 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admins should be able to delete recipe | 2 | 1 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 11 | 0
Create recipe | 2 | 1 | Planned | 2023-03-01 | Abdullah, Tarık | 1 | 2
Users shall able to create a recipe with an image | 2 | 1 | Planned | 2023-03-01 | Abdullah, Tarık | 1 | 2
Edit recipe | 2 | 3 | Planned | 2023-03-01 | Abdullah, Tarık | 2 | 0 | uc_specifications.docx
Do the design | 1 | 1 | Planned | 2023-03-01 | Abdullah, Tarık | 0.5 | 0
Do the implementation | 1 | 1 | Planned | 2023-03-01 | Abdullah, Tarık | 2023-05-01 | 0
Do the testing | 1 | 1 | Planned | 2023-03-01 | Abdullah, Tarık | 0.5 | 0
Prepare Iteration Plan for Iteration 4 | 1 | 2 | Planned | 2023-03-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Delete recipe | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 2 | 0 | uc_specifications.docx
Do the design | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 0.5 | 0
Do the implementation | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 2023-05-01 | 0
Do the testing | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 0.5 | 0
Logout Functionality | 1 | 3 | New | 2023-04-01 | Abdullah, Tarık | 3 | 0 | systemwide_req_spec.docx
Do the design | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
Do the implementation | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
Do the testing | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
Display recipe details | 2 | 3 | New | 2023-04-01 | Abdullah, Tarık | 2 | 0 | systemwide_req_spec.docx
Do the design | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
Do the implementation | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
Do the testing | 1 | 1 | New | 2023-04-01 | Abdullah, Tarık | 1 | 0
Prepare Iteration Plan for Iteration 5 | 1 | 2 | New | 2023-04-01 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Delete profile | 1 | 8 | New | 2023-01-02 | Abdullah, Tarık | 5 | 0
Do the design | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
Do the implementation | 1 | 5 | New | 2023-01-02 | Abdullah, Tarık | 3 | 0
Do the testing | 1 | 2 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
View profile | 1 | 8 | New | 2023-01-02 | Abdullah, Tarık | 5 | 0
Do the design | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
Do the implementation | 1 | 5 | New | 2023-01-02 | Abdullah, Tarık | 3 | 0
Do the testing | 1 | 2 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
Follow a user | 1 | 3 | New | 2023-01-02 | Abdullah, Tarık | 2 | 0 | uc_specifications.docx
Do the design | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 0.5 | 0
Do the implementation | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 1 | 0
Do the testing | 1 | 1 | New | 2023-01-02 | Abdullah, Tarık | 0.5 | 0
Admins should be able to send system-wide notifications | 2 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0
Create password reset page. | 2 | 7 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0
Do the design | 2 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Do the implementation | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
Do the testing | 2 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Update profile (Edit) | 2 | 8 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0 | uc_specifications.docx
Do the design | 2 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Do the implementation | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
Do the testing | 2 | 2 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Search and filter recipe (Browse) | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0 | uc_specifications.docx
Comment recipe | 2 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | uc_specifications.docx
Rate recipe | 2 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | uc_specifications.docx
Create a user settings page. | 3 | 7 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0
Do the design | 3 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Do the implementation | 3 | 5 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0
Do the testing | 3 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Calculate recipe costs | 3 | 8 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 5 | 0 | systemwide_req_spec.docx
Show recipe costs | 3 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | systemwide_req_spec.docx
Save a recipe for offline viewing | 4 | 3 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0
Prepare Iteration Plan for Iteration 6 | 1 | 1 | New | 2023-01-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
System availability | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 4 | 0 | systemwide_req_spec.docx
Monitor server uptime | 1 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Set up automated alerts for any system downtime | 1 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Implement regular database backups | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Do the testing | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
System performance | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | systemwide_req_spec.docx
Optimize server response times | 1 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Perform regular stress and load tests | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Do the testing | 1 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admins should be able to view all user activity logs | 2 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admins should have a dashboard for monitoring system metrics | 2 | 5 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Send a DM to a user | 2 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0 | systemwide_req_spec.docx
System notifications | 2 | 8 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0 | uc_specifications.docx
Admins should be able to reply to complaints | 3 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Report misuse | 3 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 2 | 0 | uc_specifications.docx
Request to be a verified account | 4 | 2 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0
Admin verifies account requests | 4 | 2 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 1 | 0 | uc_specifications.docx
Create a bonus system for the influencers | 5 | 3 | New | 2023-02-02 | Abdullah, Aslı, Merve, Tarık | 3 | 0

## Sheet2
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-01
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-01-02
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-01
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-02-02
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-03-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01
2023-04-01