## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assig-ned To | Effort estimate left (hours) | Hours worked | Reference material
Define system admins | 1 | 1 | New |  |  |  |  | Requirements.docx
Authorize admins | 1 | 3 | New |  |  |  |  | Requirements.docx
Admins should be able to create new admin user | 1 | 3 | New
Admins should be able to edit user | 1 | 3 | New
Admins should be able to delete user | 1 | 1 | New
Admins should be able to edit recipe | 1 | 3 | New
Admins should be able to delete recipe | 1 | 1 | New
Admins should be able to view all user activity logs | 1 | 5 | New
Admins should be able to reply to complaints | 1 | 3 | New
Admins should be able to reset passwords | 1 | 1 | New
Admins should have a dashboard for monitoring system metrics | 1 | 5 | New
Admins should be able to send system-wide notifications | 1 | 3 | New
System availability | 1 | 5 | New |  |  |  |  | Requirements.docx
Monitor server uptime | 1 | 3 | New
Set up automated alerts for any system downtime | 1 | 3 | New
Implement regular database backups | 1 | 5 | New
System performance | 1 | 5 | New |  |  |  |  | Requirements.docx
Optimize server response times | 1 | 3 | New
Perform regular stress and load tests | 1 | 5 | New
Ensure database security | 1 | 8 | New |  |  |  |  | Requirements.docx
User passwords should have a secure hashing algorithm | 1 | 5 | New
Database should be encrypted | 1 | 8 | New
Set up a firewall | 1 | 8 | New
Secure APIs with authentication tokens | 1 | 5 | New
Ensure HTTPS security | 1 | 5 | New |  |  |  |  | Requirements.docx
Create user register page | 1 | 3 | New |  |  |  |  | Requirements.docx
Do the design |  |  | New
Create login page | 1 | 3 | New |  |  |  |  | Requirements.docx
Do the design |  |  | New
Create password reset page. | 2 | 3 | New
Do the design |  |  | New
Create a user settings page. | 3 | 3 | New
Do the design |  |  | New
Create logout page | 1 | 2 | New |  |  |  |  | Requirements.docx
Create profile | 1 | 3 | New |  |  |  |  | uc_specifications.docx
Update profile | 2 | 3 | New |  |  |  |  | uc_specifications.docx
Create home page | 1 | 8 | New |  |  |  |  | Requirements.docx
Prototype UI |  |  | New
Do the design |  |  | New
Create recipe | 1 | 3 | New |  |  |  |  | uc_specifications.docx
Update recipe | 2 | 3 | New |  |  |  |  | uc_specifications.docx
Delete recipe | 1 | 1 | New |  |  |  |  | uc_specifications.docx
Search recipe | 2 | 5 | New |  |  |  |  | uc_specifications.docx
Save a recipe for offline viewing | 4 | 3 | New
Rate recipe | 2 | 5 | New |  |  |  |  | uc_specifications.docx
Display recipe details | 2 | 3 | New |  |  |  |  | Requirements.docx
Comment recipe | 2 | 3 | New |  |  |  |  | uc_specifications.docx
Calculate recipe costs | 3 | 8 | New |  |  |  |  | Requirements.docx
Show recipe costs | 3 | 3 | New |  |  |  |  | Requirements.docx
System notifications | 2 | 8 | New |  |  |  |  | uc_specifications.docx
Follow a user | 1 | 3 | New |  |  |  |  | uc_specifications.docx
Interact with a user | 2 | 3 | New |  |  |  |  | Requirements.docx
Report misuse | 1 | 3 | New |  |  |  |  | uc_specifications.docx
Update to the verified account | 4 | 3 | New |  |  |  |  | uc_specifications.docx
User Interface Requirements Compilancy | 5 | 1 | New
Consistency Requirements Compilancy | 5 | 1 | New
User Personalization & Customization Requirements Compilancy | 6 | 1 | New
Interfaces to other software | 6 | 1 | New